## Entrust DC Track
Transition Deliverables
Tower | Transition SME | BAU SPOC | Fuctional Manager | SMTD Status | SOP (Available / Prepared) | SOP Status for Prepared | Risk Register | RACI | SMTD / RACI (Entrust Link) | SOP (Entrust Link) | Risk Register (Entrust Link) | Approval Evidence
Timeline |  |  |  | 2025-02-15 | 2025-02-10 | 2025-02-15 | 2025-02-10 | 2025-01-06
Windows | Ajit Pandharmushe | Ravindra Rokade | Gerald Gould | in TSG Review | 8 / 2 | in TSG Review | in TSG Review | Signed Off | SMTD | Wintel SOP | Risk Register | Artifacts
Active Direcotory | Ajit Pandharmushe | Nilesh Sankpal | Matt Cousineau | in TSG Review | 10 / 0 | in TSG Review | in TSG Review | Signed Off | SMTD | AD SOP | Risk Register | Artifacts
VMware | Perisetla Chandru | Ravindra Rokade | Brian Sander | in TSG Review | 8 / 4 | in TSG Review | in TSG Review | Signed Off | SMTD | VMware SOPs | Risk Register | Artifacts
Linux | Jitendra Kumar | Merila Aditya | Gerald Gould | in TSG Review | 0 / 5 | in TSG Review | in TSG Review | Signed Off | SMTD | Linux SOPs | Risk Register | Artifacts
Backup | Veerabathran D | Soumya Ranjan Dash | Gerald Gould | in TSG Review | 3 / 1 | in TSG Review | in TSG Review | Signed Off | SMTD | Backup SOP | Risk Register | Artifacts
Storage | Santhana Krishnan | D Satya | Gerald Gould | in TSG Review | 0 / 5 | in TSG Review | in TSG Review | Signed Off | SMTD | Storage SOP | Risk Register | Artifacts
Cloud | Prasad Deshpande | Nilesh Sankpal | Gerald Gould | Not Applicable | 0 / 4 | Customer Review | No Risk Identified | Signed Off | RACI | Cloud SOP | NA | Artifacts
Messaging | Kavikumar K | Satish S | Matt Cousineau | in TSG Review | 7 / 4 | in TSG Review | in TSG Review | Signed Off | SMTD | MSG SOPs | Risk Register | Artifacts
Database | Kalpesh Bangar | Arunprasad | Joe Adam | Customer Signed Off | 4 / 11 | in TSG Review | Signed Off by Customer | Signed Off | SMTD | MSSQL SOP | Risk Register | Artifacts
Network Data | Shivesh K | Madhavaraj G | Mark Hoss | in TSG Review | 0 / 7 | in TSG Review | in TSG Review | Signed Off | SMTD | Network SOP | Risk Register | Artifacts
Network Voice | Aamer Siddique | Sunil V | Mike Tormanen | in TSG Review | 0 / 9 | in TSG Review | No Risk Identified | Signed Off | SMTD | NV SOP | NA | Artifacts